CareLoop

Detailed 3-Person Development Plan

20-hour hackathon plan | Python · FastAPI · Supabase PostgreSQL · Pydantic · LangChain + Groq

# Purpose

This document assigns concrete responsibilities, hourly tasks, integration checkpoints, acceptance tests and delivery rules for a three-person team building CareLoop. It follows the shared technical contract: backend state is authoritative, the frontend uses FastAPI, and AI proposes structured outputs but never independently verifies completion or bypasses dependencies.

# Primary outcome

Demonstrate one complete workflow: an ECG action is verified complete; its result handoff to Cardiology remains unacknowledged; the backend creates an overdue exception; the coordinator dashboard shows the gap; a simulated acknowledgment is processed; the exception is resolved and audited; and a dependent review action becomes READY only if all prerequisites are satisfied.

# 1. Team roles at a glance

| Person | Primary ownership | Core deliverables |
| --- | --- | --- |
| Person 1 — Backend | FastAPI, Supabase, shared Pydantic schemas, workflow state machine, dependencies, events, handoffs, exceptions, audit, integration. | Runnable API; persisted state transitions; seed data; backend tests; startup documentation. |
| Person 2 — Frontend | Existing frontend framework, coordinator dashboard, care journey, exception queue, acknowledgment simulator, API client and demo UX. | Dashboard using real API data; loading/error states; persisted state visible after refresh. |
| Person 3 — AI and test support | LangChain + Groq classification, Pydantic AI outputs, fallback behavior, synthetic fixtures, AI tests and optional plan extraction. | Validated message classifier; deterministic fallback; tests proving AI is optional and cannot directly mutate workflow state. |

# 2. Non-negotiable team rules

Backend owns workflow state. The frontend cannot independently mark actions complete, exceptions resolved or dependent actions ready.

Use exact canonical status and event values from the shared contract.

All state-changing routes call the same event/workflow service; do not duplicate business rules across endpoints.

The frontend talks to FastAPI, never writes directly to Supabase.

AI returns validated proposals. It cannot independently verify completion, approve a care plan or bypass dependencies.

All three developers use the same synthetic patient, plan, action, handoff and event IDs.

Inspect the current Supabase schema before migrations. Adapt existing tables instead of blindly recreating them.

Core workflow must function with Groq unavailable.

Every integration checkpoint must produce a runnable build.

Feature freeze at Hour 17; remaining time is for stabilization and demo rehearsal.

# 3. Person 1 — Backend and workflow engine

## Responsibilities

Inspect the repository, Python version, current app structure and Supabase schema.

Own migrations and database consistency.

Set up FastAPI, environment configuration, database access, health check and standard response/error models.

Own shared Pydantic event/request models.

Implement the state machine, dependency evaluation, event idempotency and validation.

Implement handoff lifecycle, overdue detection, exception management and audit history.

Expose contract endpoints and provide seed data/startup instructions.

Integrate the frontend and AI modules.

## Recommended layout

app/
  main.py
  api/
    health.py
    care_plans.py
    care_actions.py
    care_events.py
    handoffs.py
    exceptions.py
    audit.py
    ai.py
  schemas/
    common.py
    events.py
    care_plans.py
    care_actions.py
    handoffs.py
    exceptions.py
  services/
    event_service.py
    state_machine.py
    dependency_service.py
    handoff_service.py
    exception_service.py
    audit_service.py
  db/
    supabase.py
    repositories.py
migrations/
tests/
docs/CONTRACT.md
requirements.txt
.env.example

Adapt this layout to the existing repository; do not duplicate folders or services that already exist.

## Hourly plan

| Time | Tasks | Deliverable / gate |
| --- | --- | --- |
| H0–1 | Inspect repo and DB tables, constraints, foreign keys and indexes. Compare actual schema with contract. Agree statuses, event schema, response envelope and stable IDs. Update docs/CONTRACT.md. | Schema comparison and frozen contract; no blind destructive migration. |
| H1–3 | Set up FastAPI startup, /api/health, environment variables, DB access, common response/error models, Pydantic event model and repeatable synthetic seed. Implement a journey read from persisted data. | App starts; /docs loads; health check and Supabase read work. |
| H3–5 | Implement GET patient care journey, GET action, GET exceptions. Match Person 2's exact response fields. Share backend URL and sample responses. | Frontend renders one real backend read. |
| H5–8 | Implement allowed state transitions, ACTION_VERIFIED and HANDOFF_ACKNOWLEDGED dependency rules, event service, idempotency, start/report/verify operations and tests. | Validated state transitions persist; invalid transitions are rejected. |
| H8–10 | Implement POST /api/care-events, handoff create/send/acknowledge, and connect convenience routes to the same event service. Return resulting state. | A UI-triggered event persists and is visible after refetch. |
| H10–13 | Implement overdue detection, one active HANDOFF_OVERDUE exception per handoff, exception updates, audit writes and dependency reevaluation. Make multi-row updates atomic. | Acknowledgment updates handoff, exception, audit and dependencies consistently. |
| H13–15 | Run the full seeded demo from a clean state. Fix integration defects. Confirm downstream readiness and audit behavior. | Complete workflow works without manual DB edits. |
| H15–17 | Regression tests and bug fixes. Remove unstable features and freeze new functionality at H17. | Critical acceptance tests pass. |
| H17–20 | Rehearse twice, verify startup and seed reset, document run steps and finalize the tested commit. | Reproducible demo and stable final branch. |

## Backend endpoint priorities

| Priority | Endpoints |
| --- | --- |
| P0 | GET /api/health; GET /api/patients/{patient_id}/care-journey; GET /api/care-actions/{action_id}; GET /api/exceptions; POST /api/care-events; POST /api/handoffs/{handoff_id}/acknowledge; GET /api/audit. |
| P1 | POST /api/handoffs; POST /api/handoffs/{handoff_id}/send; action start/report-completion/verify-completion; exception patch/update. |
| P2 | Care-plan parse/approval and optional AI extraction persistence, if the demo can already run. |

## Backend minimum tests

Valid event causes the expected transition; invalid transition returns 409 INVALID_STATE_TRANSITION.

Unmet prerequisites prevent READY; patient report does not create VERIFIED_COMPLETE.

Unauthorized verification is rejected; required evidence is checked.

Same event ID and payload do not repeat changes; same ID with different payload returns IDEMPOTENCY_CONFLICT.

Overdue handoff creates one active exception; acknowledgment resolves it and writes audit history.

Dependent action is reevaluated after acknowledgment.

Multi-row failures do not leave partial or contradictory state.

# 4. Person 2 — Frontend and coordinator dashboard

## Responsibilities

Inspect and preserve the existing frontend framework and working code.

Build the coordinator's patient journey, action list and exception queue.

Display statuses, dependencies, responsible roles and due dates.

Build the handoff acknowledgment simulator for the demo.

Create one centralized API client and consume FastAPI only.

Handle loading, empty, success and error states.

Refresh from authoritative backend data after state-changing requests.

Make the gap, owner and next action obvious in a short demo.

## Suggested screen structure

Header: CareLoop Coordinator, synthetic patient, plan status and refresh time.

Summary: action count and open exception count.

Care journey: ECG, handoff status and dependent Cardiology review.

Exception panel: reason, assigned role, linked action/handoff and status.

Simulator: button to send a synthetic acknowledgment through the API.

Activity/audit panel: recent state-changing events.

All displayed statuses must come from the API. The frontend must not invent READY or RESOLVED after a click.

## Hourly plan

| Time | Tasks | Deliverable / gate |
| --- | --- | --- |
| H0–1 | Inspect frontend framework, entry point, routing and current components. Agree exact API envelope and response fields with Person 1. | Screen outline and API field map. |
| H1–3 | Build header, patient journey, action list, exception queue and details using contract-shaped mock data. | Navigable dashboard shell. |
| H3–5 | Create centralized API client. Implement journey, exception and action reads. Parse common success/error envelope; add loading/empty/error states. | Journey and exceptions load from FastAPI. |
| H5–8 | Add action detail, owners, due dates, dependency explanation and supported exception controls. Add refresh behavior and error messages. | Coordinator can inspect the gap and next step. |
| H8–10 | Add acknowledgment simulator using the real API. Show pending state; refetch journey, exceptions and audit after success. | UI action persists state and reflects the result. |
| H10–13 | Show ACKNOWLEDGED handoff, RESOLVED exception and backend-reported downstream status. Add audit timeline and test repeated clicks/errors. | Complete visible exception-resolution loop. |
| H13–15 | Run the scenario from a clean seed. Remove fake success states and stale mock data. Make the missing handoff and owner obvious. | End-to-end dashboard freeze candidate. |
| H15–17 | Fix layout, labels and error states; stop new feature work at H17. | Stable UI. |
| H17–20 | Rehearse twice with Person 1; verify startup, API URL and final UI state. | Presentation-ready dashboard. |

## Suggested API client methods

getHealth()
getCareJourney(patientId)
getCareAction(actionId)
getExceptions(filters)
acknowledgeHandoff(handoffId, payload)
getAudit(entityType, entityId)
reportCompletion(actionId, payload)

## Frontend acceptance tests

Dashboard renders API data, not fixed mock records.

Empty exception list and API failures render cleanly.

Acknowledgment uses the correct handoff ID and payload.

Repeated clicks do not create misleading success feedback.

After acknowledgment, handoff, exception, audit and dependent action data refresh.

No direct Supabase writes and no frontend-only status values.

# 5. Person 3 — AI workflows, structured outputs and test support

## Responsibilities

Implement LangChain + Groq message-intent classification.

Validate all model output using Pydantic.

Implement deterministic fallback for missing keys, timeouts and malformed output.

Build synthetic message fixtures and edge-case tests.

Keep classification separate from event processing and state mutation.

Optionally implement care-plan extraction into proposed actions after core integration works.

Support end-to-end testing and demo rehearsal.

## AI feature priority

| Priority | Feature | Rule |
| --- | --- | --- |
| P0 | Pydantic output schema | Required; reject unknown intents and invalid confidence. |
| P0 | Message classification | One core AI feature. |
| P0 | Fallback and error handling | Core workflow must work without Groq. |
| P1 | Synthetic fixtures and tests | Required for reliable integration. |
| P1 | Human-review flag | AI result is a proposal, not an authorization. |
| P2 | Care-plan extraction | Optional; output proposals only. |
| P3 | RAG/vector DB/multi-agent orchestration | Out of scope for the 20-hour MVP. |

## Hourly plan

| Time | Tasks | Deliverable / gate |
| --- | --- | --- |
| H0–1 | Agree intent labels, request/response shape and safety boundaries with Persons 1 and 2. Create synthetic message dataset. | Frozen AI contract and fixtures. |
| H1–3 | Define Pydantic output model, allowed intents, LangChain/Groq call and deterministic fixture-based classifier. | Validated structured output independently of frontend/database. |
| H3–5 | Test completion, barrier, reschedule, question, unclear; test missing fields, invalid labels, malformed output and no API key. | AI function returns valid schema or controlled fallback. |
| H5–8 | Implement AI service and POST /api/ai/classify-message integration. Return intent, action ID if appropriate, confidence and review flag. | Synthetic message returns validated classification. |
| H8–10 | Agree intent-to-proposed-event mapping with Person 1. Keep classification separate from event processing; validate actor and action in backend. | AI assists but does not own workflow state. |
| H10–13 | Test ambiguous messages, wrong action references, URGENT_CONCERN and invalid output. Add optional plan extraction only if core flow is stable. | Resilient AI boundary. |
| H13–15 | Run tests with live Groq if available and with AI disabled. Share stable example with Person 2. | Core workflow passes in both modes. |
| H15–17 | Fix schema/fallback defects and freeze AI changes. | Stable optional AI feature. |
| H17–20 | Support rehearsal, verify no-key path and freeze prompts/schema. | Reliable demo and documented setup. |

## Suggested AI schema

from typing import Literal
from uuid import UUID
from pydantic import BaseModel, ConfigDict, Field

Intent = Literal[
    "COMPLETION_REPORTED",
    "BARRIER_REPORTED",
    "RESCHEDULE_REQUESTED",
    "QUESTION",
    "URGENT_CONCERN",
    "UNCLEAR",
]

class MessageClassification(BaseModel):
    model_config = ConfigDict(extra="forbid")
    intent: Intent
    action_id: UUID | None = None
    confidence: float = Field(ge=0.0, le=1.0)
    requires_human_review: bool = True

## AI acceptance tests

Unknown intent and confidence outside [0, 1] fail validation.

Malformed output, timeout and missing key do not crash the app.

URGENT_CONCERN is flagged for safe human escalation, not a clinical decision.

Classifier does not mutate the database directly.

Proposed event still passes backend validation.

Plan extraction never auto-approves a care plan.

# 6. Shared API and database agreement

## Canonical statuses

| Entity | Allowed values |
| --- | --- |
| Care plan | DRAFT, PENDING_APPROVAL, APPROVED, SUPERSEDED, CANCELLED |
| Care action | PENDING, READY, IN_PROGRESS, AWAITING_VERIFICATION, VERIFIED_COMPLETE, BLOCKED, CANCELLED |
| Handoff | PENDING, SENT, ACKNOWLEDGED, REJECTED, CANCELLED |
| Exception | OPEN, IN_PROGRESS, RESOLVED, DISMISSED |
| Event processing | RECEIVED, PROCESSED, REJECTED |

OVERDUE is derived, not a care-action status. A patient report is not verification; action completion and handoff acknowledgment are separate.

## Response envelope

{
  "success": true,
  "data": {},
  "meta": {"request_id": "req-example-001"},
  "error": null
}

## Canonical event example

{
  "event_id": "e25b4dc0-5fc7-4a3e-9c39-69e9acbe0301",
  "event_type": "HANDOFF_ACKNOWLEDGED",
  "action_id": "aaaaaaaa-aaaa-4aaa-8aaa-aaaaaaaaaaaa",
  "handoff_id": "bbbbbbbb-bbbb-4bbb-8bbb-bbbbbbbbbbbb",
  "source": "DEPARTMENT_SIMULATOR",
  "actor": {"id": "demo-cardiology", "role": "CARDIOLOGY"},
  "occurred_at": "2026-10-13T08:00:00Z",
  "payload": {"receipt_reference": "DEMO-RESULT-001"}
}

Use seeded UUIDs that exist in the database. In production, derive actor identity and permissions from authentication rather than trusting client-supplied roles.

# 7. Shared 20-hour schedule and integration gates

| Time | Shared goal | Acceptance gate |
| --- | --- | --- |
| H0–1 | Contract freeze, schema inspection, shared IDs | No unresolved status, API field or ownership disagreements. |
| H1–3 | Backend foundation, dashboard mock, AI schema | Each module runs independently. |
| H3–5 | Checkpoint 1 | Real API read displayed in UI; AI schema validates. |
| H5–8 | State machine, exception interactions, classifier | A state transition persists. |
| H8–10 | Checkpoint 2 | UI-triggered state change persists; AI isolated from state mutation. |
| H10–13 | Exception resolution, audit, dependencies | Acknowledgment updates related state consistently. |
| H13–15 | End-to-end checkpoint | Full demo works from clean seed without manual DB edits. |
| H15–17 | Regression and feature freeze | Critical acceptance tests pass. |
| H17–20 | Rehearsal and release | Two clean rehearsals and reproducible startup. |

Checkpoint rule: if a gate fails, cut optional scope immediately. Do not move all later deadlines to accommodate an unfinished feature.

# 8. Git workflow and ownership

main
  └── develop
       ├── feature/backend-core
       ├── feature/coordinator-dashboard
       └── feature/ai-workflows

main is stable and demo-ready; develop is the integration branch.

Commit small runnable increments; test before merging.

After a merge, update from develop and rerun relevant tests.

Do not silently rename a status, endpoint or response field.

Person 1 owns shared schemas, migrations, state machine and final integration.

Promote develop to main only after end-to-end acceptance.

## Suggested commit messages

feat(api): add care journey endpoint
feat(workflow): implement dependency evaluation
feat(ui): add exception queue
feat(ai): add message classification schema
test(events): cover duplicate event handling
fix(handoff): prevent duplicate active exceptions
docs(contract): document acknowledgment payload

# 9. Environment and startup

Pin compatible dependency versions after checking the repository and Python version. Person 1 owns requirements.txt; Person 3 should coordinate AI dependency changes.

fastapi
uvicorn
pydantic
supabase
python-dotenv
pytest
httpx
langchain
langchain-groq

## .env.example

SUPABASE_URL=
SUPABASE_KEY=
GROQ_API_KEY=
API_BASE_URL=http://localhost:8000

Never commit real keys or expose a privileged Supabase service-role key to the browser.

## Startup commands (verify against existing repo)

python -m venv .venv
pip install -r requirements.txt
uvicorn app.main:app --reload
pytest -q

# 10. Cross-team integration tests

| Test | Action | Expected result |
| --- | --- | --- |
| T1 | Load seeded patient | Journey and plan are returned. |
| T2 | Read ECG action | Correct persisted state is returned. |
| T3 | Submit patient completion report | AWAITING_VERIFICATION, not VERIFIED_COMPLETE. |
| T4 | Submit invalid transition | Structured error; no partial mutation. |
| T5 | Leave sent handoff overdue | One active overdue exception. |
| T6 | Refresh dashboard | Same persisted exception remains visible. |
| T7 | Acknowledge handoff | Handoff becomes ACKNOWLEDGED. |
| T8 | Read exception and audit | Exception resolved and audit entry exists. |
| T9 | Read dependent action | READY only if all prerequisites are met. |
| T10 | Replay same event ID and payload | No duplicate state changes. |
| T11 | Reuse event ID with different payload | IDEMPOTENCY_CONFLICT. |
| T12 | Disable Groq | Core workflow remains usable. |
| T13 | Submit malformed AI output | Safe validation/fallback behavior. |
| T14 | Restart and reload journey | Persisted state remains correct. |

The acknowledgment operation should validate actor and handoff, record the event, update handoff status, resolve the applicable exception, write audit history and reevaluate dependencies atomically. Multiple independent Supabase client calls are not automatically one transaction; use a PostgreSQL transaction or database function/RPC.

# 11. Main demo script

Person 1 seeds synthetic data: ECG is VERIFIED_COMPLETE; the result handoff is SENT but unacknowledged; Cardiology review is PENDING.

Trigger overdue monitoring or the deterministic demo trigger. Backend creates one HANDOFF_OVERDUE exception.

Person 2 opens the dashboard and shows the missing acknowledgment, responsible role and affected action.

Person 2 clicks the simulated acknowledgment control. FastAPI validates and processes the event.

Show handoff ACKNOWLEDGED, exception RESOLVED and an audit record. The dependent review becomes READY only if all prerequisites are met.

If time permits, Person 3 classifies a synthetic barrier message and then demonstrates that the main workflow still works with AI disabled.

# 12. Failure response and scope-cutting rules

| Failure | Response |
| --- | --- |
| Schema differs from contract | Adapt to existing schema; do not reset blindly. |
| Frontend waiting on API | Publish agreed route/response shape; frontend uses matching fixtures meanwhile. |
| Different UUIDs in branches | Freeze a shared seed fixture and IDs. |
| Groq unavailable | Disable optional AI and continue the core workflow. |
| UI state disappears after reload | Prioritize persistence/API reads over new features. |
| Duplicate exceptions | Fix idempotency and active-exception uniqueness. |
| Dependent action remains pending | Inspect prerequisites and dependency evaluator; do not force READY. |
| Partial multi-row updates | Use a transaction or database function/RPC. |
| End-to-end flow not working by H13 | Cut optional features and focus on demo by H15. |
| Bugs remain at H17 | Freeze features; use remaining time for fixes and rehearsal. |

# 13. Final deliverables checklist

## Person 1 — Backend

FastAPI starts and Supabase reads work.

Canonical Pydantic schemas and response envelope.

State machine and dependency evaluator.

Event idempotency and handoff lifecycle.

Exception detection, resolution and audit.

Seed data, startup commands and backend tests.

## Person 2 — Frontend

Coordinator dashboard and care journey.

Exception queue and clear ownership display.

Centralized API client.

Acknowledgment simulator calls the real API.

UI refreshes persisted state and audit history.

Loading/error states and demo polish.

## Person 3 — AI and test support

Pydantic AI output schema and LangChain + Groq classifier.

Synthetic message fixtures.

Fallback and malformed-output handling.

AI cannot directly mutate or verify workflow state.

AI outage tests; optional extraction only if time permits.

## Whole-team acceptance

All developers use the same contract and seed IDs.

End-to-end workflow works from a clean start.

Duplicate-event and invalid-transition tests pass.

Core workflow works with AI disabled.

Two successful demo rehearsals are complete.

# 14. Final recommendation

Person 1 owns correctness; Person 2 owns visibility and interaction; Person 3 owns optional intelligence and resilience. The highest-risk work is the consistency of state transitions, handoff acknowledgment, exception resolution, audit history and dependency reevaluation. Protect the Hour 5, Hour 10 and Hour 15 integration deadlines. If a deadline slips, reduce scope instead of adding components.